## Basic Project Template
|  |  |  | Business Analyst (BA) with Solution Designing skills | Technical Consultant (DEV) Is a developer that will configure and integrate
| Content Hub One |  |  |  |  | Project
| This is example Content Hub One project that can be used as a template for Partner teams to use in their implementations. This estimation is based on 2-3 content types/models and integrating headless output into at least 2 external solutions. |  |  |  |  | Management
20%
Phase# | Phases | Task | Topic & Task Description | Effort in hh
1 | Discovery: Kickoff and Planning | # | Tasks | BA | DEV | PM(***) | Total hh | Comments
|  | 1 | Determine access to Content Hub One | 2
|  | 2 | Provide instruction accessing education resources | 1
|  | 3 | Determine Content Model Schema | 8
|  | 4 | Determine Content Types | 4
|  | 5 | Understand all the external solutions that will require integration | 2 | 4
|  | 6 | Evaulate any third party integrations | 2 | 4
|  | 7 | Determine the amount of media (assets) that will be used for Content | 1
Total Hours
2 | Configuration/UAT | 1 | Configure the Content Model |  | 6
|  | 2 | Configure the Content Types |  | 2
|  | 3 | Configure API Keys |  | 1
|  | 4 | Configure GraphQL Queries |  | 4
|  | 5 | Integrate GraphQL points into external solutions |  | 16
|  | 6 | UAT - Validate configuration |  | 2
|  | 7 | UAT - Validate external solutions |  | 2
Total Hours
3 | Use Case Specific Go-live (Pre and Post) | 1 | Hand-Over Documentation (Setup client to put in support tickets) | 3 | 4
|  | 2 | Burn In Support | 8 | 16
|  |  |  | 31 | 61 | 18.4 | 110.4

## Complex Project Template
|  |  |  | Business Analyst (BA) with Solution Designing skills | Technical Consultant (DEV) Is a developer that will configure and integrate
| Content Hub One |  |  |  |  | Project
| This is example Content Hub One project that can be used as a template for Partner teams to use in their implementations. This estimation is based on 10-15 content types/models, integrating headless output into at least 5 external solutions and one thrid party integration into Conte Hub One. |  |  |  |  | Management
20%
Phase# | Phases | Task | Topic & Task Description | Effort in hh
1 | Discovery: Kickoff and Planning | # | Tasks | BA | DEV | PM(***) | Total hh | Comments
|  | 1 | Determine access to Content Hub One | 2
|  | 2 | Provide instruction accessing education resources | 1
|  | 3 | Determine Content Model Schema | 40
|  | 4 | Determine Content Types | 20
|  | 5 | Understand all the external solutions that will require integration | 10
|  | 6 | Evaulate any third party integrations | 8 | 16
|  | 7 | Determine the amount of media (assets) that will be used for Content | 10
Total Hours
2 | Configuration/UAT | 1 | Configure the Content Model |  | 32
|  | 2 | Configure the Content Types |  | 4
|  | 3 | Configure API Keys |  | 2
|  | 4 | Configure GraphQL Queries |  | 20
|  | 5 | Integrate GraphQL points into external solutions |  | 32
|  | 6 | UAT - Validate configuration |  | 10
|  | 7 | UAT - Validate external solutions |  | 10
Total Hours
3 | Use Case Specific Go-live (Pre and Post) | 1 | Hand-Over Documentation (Setup client to put in support tickets) | 6 | 16
|  | 2 | Burn In Support | 8 | 16
|  |  |  | 105 | 158 | 52.6 | 315.6

## Migration Project Template
|  |  |  | Business Analyst (BA) with Solution Designing skills | Technical Consultant (DEV) Is a developer that will configure and integrate
| Content Hub One |  |  |  |  | Project
| This is example Content Hub One project that can be used as a template for Partner teams to use in their implementations. This estimation is based on 10-15 content types/models, integrating headless output into at least 5 external solutions and one thrid party integration into Conte Hub One. This also includes a migration of pre-existing content that the client wants to import. This will require the DEV team to determine the amount of content items and assets, which will require customized development work to make a console application to map and import the content using the SDK. The migration estimate based against 20K content/asset items. |  |  |  |  | Management
20%
Phase# | Phases | Task | Topic & Task Description | Effort in hh
1 | Discovery: Kickoff and Planning | # | Tasks | BA | DEV | PM(***) | Total hh | Comments
|  | 1 | Determine access to Content Hub One | 2
|  | 2 | Provide instruction accessing education resources | 1
|  | 3 | Determine Content Model Schema | 40
|  | 4 | Determine Content Types | 20
|  | 5 | Understand all the external solutions that will require integration | 10
|  | 6 | Evaulate any third party integrations | 8 | 16
|  | 7 | Determine the amount of media (assets) that will be used for Content | 10
|  | 8 | Determine the amount of content and map fields to new schema(s) | 10 | 16
Total Hours
2 | Configuration/UAT | 1 | Configure the Content Model |  | 32
|  | 2 | Configure the Content Types |  | 4
|  | 3 | Configure API Keys |  | 2
|  | 4 | Configure GraphQL Queries |  | 20
|  | 5 | Integrate GraphQL points into external solutions |  | 32
|  | 6 | UAT - Validate configuration |  | 10
|  | 7 | UAT - Validate external solutions |  | 10
|  | 8 | Create console application to map and import Content and Assets into instance |  | 30
|  | 9 | Validate test Import mapping and items | 10 | 10
Total Hours
3 | Use Case Specific Go-live (Pre and Post) | 1 | Hand-Over Documentation (Setup client to put in support tickets) | 6 | 16
|  | 2 | Import of 20K Content/Assets into Content Hub One | 8 | 120
|  | 3 | Burn In Support | 8 | 16
|  |  |  | 133 | 334 | 93.4 | 560.4